## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
s1 | s1 | All | Take a Research survey about the different techniques for implementing traffic management and surveillance system | Must Have | arXiv Papers | Soham | 3- Completed
s1 | s1 | US-ID 01,US-ID 02 | Gather the Requirements and understand the problems like traffic violation, road congestion at rush hour and managing the traffic as per the vehicle class. | Should Have |  | Soham | 3- Completed
s1 | s1 | US-ID 03 | For this problems we make a one workflow which is based on the Automatic traffic control and count (ATCC) and Automatic Number Plate recognition (ANPR) for managing the Traffic Rule violation. | Should Have |  | Soham | 3- Completed
s2 | s2 | US-ID 01 | In Workflow we plane to develop three different YOLO based model for this website. 1,vehicle class predection, 2.Traffic violation detection, 3.Vehicle Number Plate detction. For this we try to gather different dataset on the internet. | Must Have |  | Soham | 3- Completed
s2 | s2 | US-ID 04 | After gathering the appropriate dataset for each model we first make some essential steps to convert the data in proper formate. | Must Have | Kaggle,Roboflow,huggingface | Soham | 3- Completed
s2 | s2 | US-ID 03 | Then we start to do data processing with the pandas and numpy to convert the data in the formate where we can do the data visualization. | Must Have | pandas, numpy | Soham | 3- Completed
| s3 | US-ID 05 | Now we start the data visualization on each dataset to understand the class distribution like for the vehicle class dataset we see the ration of two-wheeler per bus is 10:1. | Should Have | Matplotlib | Soham | 3- Completed
| s3 | US-ID 06 | After getting this important the understanding about the data set we try to adjust it to make more generalize models which are capable for real life scenarios. | Should Have | Scikit-learn | Soham | 3- Completed
s3 | s3 | US-ID 07 | After adjusting the Data Distribution we start the data transformation for the model development. As we are going with the YOLO model we convert some of our labels in to this specific formate and also for the numeric range adjustment we make sure numeric features are follow normal distribution. | Must Have | Scikit-learn | Soham | 3- Completed
s4 | s4 | US-ID 04 | Then we research about the different yolo version their specific pros and cons for specific problem like for the vehicle class detection we go with the YOLOv9 and for traffic violation we go through YOLOv8. | Should Have | YOLO Documentation | Soham | 3- Completed
s4 | s4 | US-ID 08 | Now we fine-tune the model which we choose on the preprocessed data and also adjust the hyper-parameter as per the specific model. | Must Have | Ultrlytics | Soham | 3- Completed
s5 | s5 | US-ID 10 | After completing the model Development we make the Python functionalities for the specific features like pixel management for the road congestion analysis. | Must Have | Python libraries | Soham | 3- Completed
s5 | s5 | US-ID 09 | Then We use the streamlit functionalities for developing the UI. | Should Have | Streamlit | Soham | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7